## RAID LOG
| RAID Log | Should you face any difficulty in completing the RAID Log, please refer to 'Project Planning' Workshop, https://cloudcounselage.graphy.com/sessions/Project-Planning-64af88dcb308530823e2c19f | [8 empty] | Total | Critical | High | Moderate | Low | Negligible
[10 empty] | Risk | 6 | 2 | 0 | 0 | 0 | 0 | Instruction to use the RAID log template: • All fields must be duly filled • The descriptions for what to be filled in each of the fields are provided in the template. • Clear all the sample data/instructions provided in the template. The data/instruction provided is only for reference purposes. • Understand what risks, assumptions, issues, and dependencies are from the description provided in the methodology document • Select the category of RAID from the dropdown menu provided in the “RAID category” field in the template. • Provide a valid description of the RAID category that you have selected in the “description” field provided. • Describe the impact the RAID category you have selected will have on the project in the “impact field”. • Describe how the impact of the selected RAID category can be reduced on the project in the “mitigation field” in the template. • Mention the responsible person for working on the selected RAID category in the “owner” field in the template. • Select the priority with which the selected RAID category needs to be mitigated. The following levels of priority are given in the drop-down menu. Select; o Negligible: if the RAID category is not going to make an impact on the project o Low: if the raid category is going to make very small impacts on the project o Moderate: if the RAID category is going to make a few impacts which can affect the project adversely. o High: if the RAID category is going to make major impacts on the project adversely. o Critical: if the raid category is going to affect the project at any stage. • Provide risk priority number based on the priority selected for the RAID category selected. • Select the status of the RAID category selected. Two options are provided in the drop-down menu. Select; o Open: if the responsible person is still working on the RAID category selected. o Closed: if the responsible person has worked on the RAID category and is solved.
| Project title: | Graduate Career Recommender System |  | Project Id: |  | Project Manager: | Harshada Topale |  |  | Assumption | 4 | 0 | 0 | 0 | 0 | 0
[10 empty] | Issue | 3 | 0 | 0 | 0 | 0 | 0
| DOCUMENT VERSION: | 1 |  | Last Updated date: | 2025-06-03 | Project Team Lead: | Pranay Sunil Jagtap |  |  | Dependency | 4 | 0 | 0 | 0 | 0 | 0
| Select … |  |  |  | Owner | Select … | Risk Priority Number | Open/Closed |  |  | 17 |  |  |  |  | 2
| RAID Category | Description | Impact | Mitigation | Owner | Priority | RPN (for risks) | Status
3 | Risk | Incorrect handling of NaN and duplicated values in the dataset | Model training errors and inacurate predictions | Use proper imputation strategies and handle NaNs or drop NaNs if necessary. Remove duplicated values | Team Lead | High | 7 | Closed | Risk
4 | Risk | The dataset is imbalanced. There is an imbalance in the target variable classes. Being a classification task, target classes must be balanced. | The model may get baised towards the majority target class and generalize poorly | Use stratified splits to ensure the target classes ratio is maintained in train, validation, and test set. Used RandomUnderSampler to balance the classes. Use StratifiedKFold for model training with Optuna. | Team Lead | Critical | 9 | Closed | Assumption
| Risk | Model Overfitting | Model or NN may overfit on the limited or imbalanced data. Lead to poor generalization on unseen data. | Use cross-validation or stratifiedkfold, oversampling or undersampling, and monitor performance metrics on train/val sets like precision, recall, and f1-score. AVOID USING ONLY ACCURACY AS A PERFORMACE METRIC IN IMBALANCED DATA CASE | Team Lead | Critical | 9 | Open
| Risk | Experiment Tracking Relaibility | MLFlow/DAGsHub tracking or artifacts logging may fail resulting in loss of expriment data | Added error handling and logging function/code blocks and | Team Lead | Moderate | 5 | Closed
| Risk | Compute resource contraints | Running Optuna hyper-parameter search or training neural networks may exceed available compute power/memory | Use batch processing, limited/lesser optuna trials, and allowed both CPU/GPU training | Team Lead | Low | 3 | Closed
| Risk | Model performance not matching the desired performance threshold even after taking required performance improvement strategies | Model with high bias, poor precision & recall values. Model predictions can not be trusted. Probability score of the predicted class is lower than 40%. False negatives (missing a suitable career path) are more detrimental than False positives. | Use precision-recall-curve to find out a threshold value which can improve models recall without compromising precision. | Project Manager/Team Lead | Critical | 9 | Open
5 | Assumption | The provided dataset have relevant features for target variable prediction | Impacts model’s capability to learn from the features, eventually resulting in poor generalization | Review the dataset and perform feature engineering and create interaction features if neccessary | Team Lead | Moderate | 6 | Closed | Issue
6 | Assumption | Students information integrity. Students self reported skills, rating, and preferences are assumed to be true and genuine. | Inaccurate self-assessment could reduce model’s recommendation quality. |  | Project Manager/Team Lead | Negligible | 0 | Closed | Dependency
7 | Assumption | Library compatibility. All libraries to be used are assumed to be compatible with each other and available in the environment. | Using incompatible libraries or version mismatch could break the code and produce inconsistent results. | Create a separate environment for the project and ensure correct library version is installed. | Team Lead | Low | 2 | Closed
8 | Assumption | Artifacts persistence. Saved artifacts, encoders, models, and metrics are available for future references and deployment purposes. | Missing artifacts would prevent reproducibiity and model deployment. | Ensure consistent artifact logging to MLFlow/DAGsHub after each experiment. | Team Lead | Moderate | 6 | Closed | Open
9 | Issue | Outlier handling. Outlier detected in numerical features. | Outliers can significantly impact model’s overall performance leading to reduced accuracy, biased predictions, and poor generalization. | Applied IQR based capping and reduced its impact by removing outliers. | Team Lead | High | 7 | Closed | Closed
10 | Issue | Categorical feature encoding. Many categorical features requires careful encoding to numbers. ML models can not process text/string data upfront. The text data needs to be encoded/converted into numeric form before feeding it to the model. | ML model may break and throw error/warning regarding passing string data without proper encoding. | Essential categorical feature encoding strategies were used like LabelEncoder and OneHotEncoder depending on categorical feature type. | Team Lead | Critical | 9 | Closed
11 | Issue | Need for comprehensive model evaluation strategy like confusion matrix, classification report, ROC and PR curves. | Helped to find out model’s performance on training and validation data. | Implemented custom plotting and evaluation functions using plotly. | Team Lead | Low | 3 | Closed | Critical
12 | Dependency | Project’s Dependencies: Scikit-learn, Pytorch, pandas, numpy, plotly, matplotlib, imblearn, mlflow, dagshub, torchmetrics, etc. | Impossible to train model without these libraries. | Installed libraries. | Team Lead | Critical | 9 | Closed | High
13 | Dependency | Data Artifacts: Encoders, model checkpoints, metrics files. Essential for reproducibility and model deployment. | Would be difficult to deploy model with similar weights as at the time of training. | Loaded artifacts and model weights from MLFlow/DAGsHub. | Team Lead | High | 7 | Closed | Moderate
14 | Dependency | Experiment Tracking URI & credentials: MLFlow/DAGsHub tracking URI and credentials for logging experiments and artifacts. | Without tracking URI and account credentials we can not log experiments and artifacts to MLFlow/DAGsHub. | Set via environment variables or Colab secrets. | Team Lead | Moderate | 5 | Closed | Low
15 | Dependency | GPU Hardware: For faster neural network training (optional) | Training NN model on CPU can be incredibly lengthy. | Code support both CPU and GPU based model training. | Team Lead | Low | 3 | Closed | Negligible
16
17
18
19
20
21
22
23
24